Northwestern University

# Monthly Status Report

Annotation and Image Markup (AIM)

12XS577

April 2013

Pattanasak Mongkolwat

p-mongkolwat@northwestern.edu

Reported: May 7, 2013

# Contents

Project Background/Objectives	2

Personnel Roster	2

Contract Overview	3

Current Project Status	3

AIM Model	3

AIM 4.0 Library and Workstation	4

Update AIM wiki pages	4

CMake and AIM 4.0	4

AIM 4.0 RESTFul interface with AIM Data Service	4

Working with QA team	5

XNAT	5

Description of Work Completed During the Month	7

External Meetings	7

Project Progress	10

Status of Milestones	10

Work Planned for Next Month	10

Travel Planned for Next Month	10

Issue Management	10

Risk Management	11

External Dependencies	11

Status of Deliverables	11

# Project Background/Objectives

The objective of this project is to continue to develop the Annotation and Imaging Markup (AIM) software library and tools based on the AIM v4.0 model to meet the challenge of targeted multiple imaging domains, including Radiology and Radiation Oncology. The AIM model establishes a solid foundation for the growth of AIM in specific areas such as clinical trials and life science. The AIM standard has demonstrated its usefulness by collecting the descriptive information of images with user-generated graphical symbols, computational results, and textual descriptors placed on the images in a single common information source. The AIM model is necessarily complex and comprehensive. Typically, users do not want to understand the model comprehensively. We consider AIM users as belonging to one of two types: end-user or software developer. We provide them with appropriate software products and a programming library along with a referenced implementation of the library.

The AIM template is designed to abstract the complexity and reduce the number of activities for both types of AIM users. A template consists of a collection of questions and corresponding answers to each question. It increases AIM usability and improves experiences for users who create AIM data in their specific domain areas.

The AIM template project has two components: AIM Template Builder (ATB) and AIM Template Service (ATS). ATB has been developed to allow creation and modification of AIM templates via a software application with a simple graphical user interface. A template constrains AIM users to consistently create structured AIM data with standardized semantic vocabulary and controlled terminologies. ATS allows AIM users to search, share, download, and upload their templates.

The outcome of the project includes the AIM 4.0 foundation model, AIM 4.0 imaging model for (but not limited to) Radiology and Oncology, AIM toolkit (library in C++ and a conversion tool), AIM workstation, and AIM template software. The AIM software products will enable imaging interpreters, image researchers, and associated sciences personnel from different domains to adopt standardized annotations and imaging markup in conducting their clinical trials and translation medicine research.

# Personnel Roster

| Personnel | Roles | Organization |
| --- | --- | --- |
| Pattanasak (Pat) Mongkolwat | Principal Investigator (PI), project manager and software engineer | Northwestern University |
| Vladimir Kleper | Researcher and software engineer | Northwestern University |
| Skip Talbot | Software engineer | Northwestern University |
| David Clunie | Consultant (DICOM, imaging and clinical expert) | PixelMed Publishing, LLC |
| Gregory Sharp | Consultant (CMake) | - |
| Daniel Rubin | Consultant (AIM and clinical expert) | Stanford University |
| Carolyn Klinger | Technical Writer | National Cancer Instittute |

# Contract Overview

The purpose of this project is to provide guidelines for extending the AIM model to enhance existing AIM tools (C++ toolkit, ATS and AIM for ClearCanvas workstation), develop additional AIM capabilities, and provide support in line with the historical workload and available resources.

The AIM project consists of the AIM information model, C++ Application Programming Interfaces (APIs), ATS, and AIM-enabled workstations. At the end of this research and development phase, we will accomplish the following.

- First, deliver a technical document on how to extend the AIM foundation model and library.

- Second, deliver the AIM C++ toolkit for Linux, OS X, and Windows platforms.

- Third, ATS shall have a Representational State Transfer (REST, RESTful conforms to REST constraints) APIs for other applications to consume ATS services.

- Fourth, AIM on ClearCanvas workstation will support creation and use of DICOM segmentation objects along with related AIM objects. The workstation will create and store AIM 4.0, import imaging studies from the eXtensible Neuroimaging Archive Toolkit (XNAT), communicate with AIM Data Service via RESTful APIs, validate markup creation and integrate a centralized imaging security service. An AIM plugin for the ClearCanvas workstation will be provided. A demonstration of the workstation installed on Amazon cloud will be provided.

- Fifth, AIM Data Object Service (DOS) will offer web services to create and manipulate AIM data.

The following tools were used in this project.

- Altova XMLSpy 2013 (Altova)

- caCORE SDK 4.1.1 (caBIG®)

- DCMTK version 3.6.x (OFFIS e. V.)

- Eclipse (Eclipse Foundation, Inc.) for Windows and Linux

- Enterprise Architect version 10.x (Sparx Systems)

- Java JDK 6 (Sun Microsystems)

- Microsoft Visual Studio 2008 and 2010 (Microsoft) with STL

- Xerces XML library version 3.0.1 (Apache Software Foundation)

- Boost C++ library version 1.34.1 (Boost.org)

- Berkeley DB XML by Oracle

- Linux OSes (Debian 6.0.x and above and Ubuntu version 11 and above)

- Mac OS X 10.7.5 (Lion)

- Xcode 4.6.x and Xcode command line utilities

- CMake 2.8.x and above

- Homebrew Package Installer for Mac OS X

# Current Project Status

## AIM Model

The EVS and AIM team validated and manually verified the AIM Foundation model, then uploaded it caDSR. AIM version 4.0 was revised based on an implementation of the AIM 4.0 C++ library. The Enterprise Vocabulary Services (EVS) team is reviewing AIM version 4 for Radiology and Oncology. The AIM team has been working with the EVS team to validate and upload the 4.0 model. The AIM team uploaded AIM 4.0 to the caDSR sandbox server and production server for verification and released it for public use.

## AIM 4.0 Library and Workstation

We are implementing the AIM 4.0 C++ library on the AIM 4.0 workstation.

## Update AIM wiki pages

We continue to update pages on the NCI Wiki as needed.

## CMake and AIM 4.0

Fixed CMake for Linux and Mac OS X.

Discussed the error when running compiled code on Ubuntu and OS X. The core cause of the issue is a race condition between static variables when they initializize in AIMLib and DCMTK. Decided to disable DCMTK logging because it uses the static variable that cause the issue. Greg made the change and it appears to work.

Windows implementation has commenced and build issues are being worked on right now. Currently, mismatched C++ runtime between DCMTK and AIMLib is being fixed.

Initial implementation of dynamically linked Linux and OS X libraries has landed. One issue remains - proper setting of -fPIC compiler flag for 64-bit Linux (and OS x?) systems.

We worked back and forth on linking and compilation issues over email.

Due to the -fPIC flag, the code still does not dynamically link on my 64-bit VM. Vlad will create a test code bundle when the issue is fixed.

Telephone conference on April 25th, 2013.

  - Greg figured out the issue with the 64-bit builds not getting the correct build flags set. The reason was that Release or Debug option was not set. He fixed build flags for general case as well as we decided to make all builds Release by default.

  - There was a question of correct case for one pre-procecessor definition. Greg will make CMake configuration to follow the Windows convention (all caps)

  - CMake configuration options will include choice between shared and static builds on Unix-like platforms. This applies to AIMLib and the AIM converter tool only.

  - Next t-con is on May 9th, 2013.

## AIM 4.0 RESTFul interface with AIM Data Service

The AIM team provided additional information, including XPath expressions, on requirement specifications to Emory. The AIM team started implementing the graphical user interface for the new AIM data service.

The AIM team had a telephone conference with the Emory team on April 10th, 2013. A summary is as follows.

  - The initial version of the new AIM Data Service will support Image Annotations only. We will talk about Annotation of Annotation support closer to the time when the workstation implements it. Annotation of Annotation AIM data service may have a different URL (TBD).

  - First version of AIM Data Service will come online in the 1st or 2nd week of May.

  - Before the AIM Data Service release, we'll get a document with draft API, query conventions, and URLs. The final deployed version may have changes.

  - The official name of the new Bindas-based AIM Data Service needs to be discussed with Ashish. Internally they call it AIME 2.0

  - AIM Data Service 2.0 only supports API Key STS authentication (no caGrid, a.k.a. Dorian support)

  - We will only have CTIA credentials for the AIM 4.0 Data Service. Anyone can register at http://cancerimagingarchive.net to get an account.

  - A new VM with AIM 3.0 Data Service (CQL) will be available this week.

  - Authorization will be available only to the middleware-based applications, i.e. those applications will have the ability to configure who has access to their internal data.

The AIM team had a telephone conference with the Emory team on April 24th, 2013. A summary is as follows.

a.	New VM with AIM Data Service 1.0 (CQL) will be available this week.

b.	Tested the workstation to retrieve AIM XML documents from AIM Data Service 1.0

i.	http://imaging.cci.emory.edu/aime-test/wsrf/services/cagrid/AIM3DataService

c.	The team modified the AimDataService plugin so that it could handle login credentials and manage API keys as they automatically expire. The plugin is ready to receive the API from Emory, which will require properly-formatted of login credentials, query strings, and parsing the results from the web service.

d.	We will only have TCIA credentials for AIM 4.0 Data Service. Anyone can register at http://cancerimagingarchive.net for an account.

e.	Authorization will be available only to the middleware-based applications, i.e. those applications will have ability to configure who has access to their internal data.

## Working with QA team

The AIM team started working with the QA team to test the AIM Workstation and CMake with the AIM 4.0 library.

  - Nadir continues to implement the AIM 4.0 Data Service and an initial version should be available in the first half of May.

  - We fixed a couple of missing attributes in the API wiki and discussed the changes to the return data. Search results will have data for all Imaging Physical Entities, Imaging Observation Entities, and their characteristics.

  - JSON query responses will preserve the original container/annotation/observation/characteristic hierarchy of data. We'll flatten the data as needed on the client.

  - Nadir will update the API wiki with real REST URLs when the work is complete.

  - We clarified that authentication will use HTTP BASIC authentication mechanism via "Authorization" HTTP header using Base64 encoding (http://en.wikipedia.org/wiki/Basic_access_authentication).

  - All Data Service APIs will support HTTP GET and POST methods.

  - The AIM team will provide Nadir with additional XPath examples for querying required elements and attributes of Imaging Physical Entities, Imaging Observation Entities, and their characteristics (uniqueIdentifier, typeCode, questionTypeCode and their attributes).

  - Working on ATS deployments on 32 and 64-bit.

## XNAT

The AIM team started working on the XNAT. XNAT interface is project and description-oriented. The GUIs proposed in the AIM_eplc_design_template_v1.2.doc are not suitable for XNAT users. Implementing the XNAT interface on the AIM workstation is very time consuming and will require additional resources.

- Need to embed the XNAT web interface for search and download.

- Download to a predefined directory (Tools->Options->AIM) to import images to the workstation automatically.

- Once the XNAT tab is activated, a process monitors the directory in C# every minute. If there is a study, the workstation imports it and deletes the folder in the directory.

- See https://tracker.nci.nih.gov/browse/AIMWS-148

Old design:

New Design:

Landing page

Login page

# Description of Work Completed During the Month

## External Meetings

| Date | Topic | Project Attendees (Optional) |
| --- | --- | --- |
| April 2013 | JIRA issues (addition and updates) | Pat, Vlad, Skip |
| April 2013 | Weekly telephone conference | Ed Helton, Jonathan Lin, Ulli Wagner, Laxmi, Tin, Vlad, Skip, Pat |
| April 2013 | Prepared and presented AIM status report to the monthly imaging community telephone conference meeting | Pat |
| April 2013 | Participated in the NCI Case Report Form Harmonization Working Group on Imaging | Pat |
| April 2013 | Exchanged e-mails with John Butman about AIM plug-in for the ClearCanvas commercial workstation | John Butman (NIH) and Pat |
| April 2013 | Worked with QA team at NCI: - Updated AIM test scope document - Exchanged and answered e-mails related to AIM products - Exchanged e-mails about AIM & CMake - Test environment - Exchanged e-mails with Tin on how-to use AIM 3.5 workstation - Exchanged e-mails with Tin on how to test the NBIA data service - Answered e-mails about ATS 1.1 and ATB 2.0 - Login - Setup, configuration, database issues - Usage - Requested Tin to properly put ATS issues in AIMES on NCI’s JIRA (Pat removed the old issues from AIMWS-149 and -150). | Tin, Laxmi, Vlad, Skip and Pat |
| April 2013 | Worked with Carolyn Klinger on - Moving older AIM content from NCI GForge to SVN - Monthly report - Exchanged e-mails about converting old AIM PDF documents to AIM NCI wiki - Removing draft status from https://wiki.nci.nih.gov/x/GACxBQ - AIM monthly report | Carolyn Klinger, Ann Wiley, Craig Fee and Pat Mongkolwat |
| April 2013 | Worked with NBIA team on GitHub - E-mail exchanges on AIM SVN and GForge issues - Provided AIM SVN and other related information for moving AIM content to GitHub, modified OSDI_ Input_Checklist_508_compliant_Pat.docx - Telephone conferences about GitHub - AIM GForge to NCI SVN https://ncisvn.nci.nih.gov/WebSVN/listing.php?repname=docs https://ncisvn.nci.nih.gov/WebSVN/listing.php?repname=files - Informed Skip’s Github account - Agreed to have AIM 3.0 and above to be moved to GitHub - AIM NCI’s SVN last update on April 25th, 2013 and informed Scott Gustafson about completion of AIM resources on the SVN - Answered Ulli’s e-mail about AIM source code repository | Scott Gustafson, Qinyan Pan, Vrushali Nikte, Ulli, Vlad, Pat |
| April 2013 | Worked with Gregory Sharp - Telephone conferences - Bug fixes for Linux and Mac OS X - Exchanged e-mails on issues related to compiling Linux and Mac OS X | Gregory Sharp, Vlad Kleper, Pat |
| April 2013 | Work with the Emory team on AIM Data Service - Worked on AIM XPath expressions and examples - Revised and sent AIM Data Service requirements document to Nadir to create APIs - Exchanged e-mails - Vlad sent a question about STS authentication and authorization - Scheduled a web conference call for April 10th at 3pm EST using Skype between Nadir and Vlad - Web conference call with Nadir on April 10th. - Worked on APIs for integration with AIME 2.0, http://imaging.cci.emory.edu/wiki/display/CXFIVIM/AIME+-+ClearCanvas+Integration - Received AIM Data Service 1.0 URL, http://imaging.cci.emory.edu/aime-test/wsrf/services/cagrid/AIM3DataService | Ashish, Nadir, Vlad, Skip and Pat |
| April 2013 | - Contacted David about the plan to implement DICOM Segmentation on AIM workstation | David Clunie and Pat |
| April 2013 | Worked with Justin Kirby (CIP) - AIM Workstation 3.5 related issues - ATS related issues | Justin Kirby and Pat |
| April 2013 | Worked with the NBIA team on retrieving imaging studies from NBIA - Exchanged e-mails with Qinyan about NBIA retrieval errors - Telephone conferences with NBIA team showing how to run the AIM workstation and test it with NBIA production and stage servers - NBIA needs to set a permission for a temporary zip file to be created for image transfer purposes - Testing activities - Attempted to create new C# interface with the new NBIA 5.1. It was not successful due to incomplete or incorrect WSDL files retrieved from NBIA. We will need help from the caGrid team if we want to add a new C# interface on caGrid. - Fixed image retrieval issue when a user attempts to retrieve imaging studies for a second time after completing the first retrieval - Reported to the NBIA team an error related to retrieving TrialDataProvenance. - Sent and received e-mails with Scott Oster and John Eisenschmidt about generating C# from WSDL files. | Qinyan Pan, Qinyan Pan, Vrushali Nikte, and Pat |
| April 2013 | - Provided AIM 4.0 examples - Provided consultation about AIM Template Builder 2.0 - Provided AIM 2.0 template examples | Daniel Rubin, Hakan Bulu, Camille Kurtz, Debra Willrett and Vlad |
| April 2013 | Participated in OSDI Kick-off meeting for imaging projects (NBIA, AIM, and IVIM) | Pat |
| April 2013 | Unscheduled telephone conference about ANIVATR tool to be used to assist Daniel’s FDA web imaging viewer - Viewer is capable of converting an AIM DICOM SR object to AIM XML documents and vice versa - Need mapping to AIM data model and programming work for other type of DICOM SR objects | Ulli, Johnathan, Daniel Rubin, Pat |
| April 2013 | Participated in TCIA REST API conference call | Pat, Vlad and Skip |

## Project Progress

| Activity | Description |
| --- | --- |
| NCI’s JIRA | Continue updating: - AIM Enterprise Service (ATB & ATS), https://tracker.nci.nih.gov/browse/AIMES - AIM Model, https://tracker.nci.nih.gov/browse/AIMWS - AIM Workstation, https://tracker.nci.nih.gov/browse/AIM |
| AIM SVN for GitHub | - Uploaded AIM 3.0, AIM foundation, AIM 4.0 and related source code to the models - Uploaded related XML schemas, documents - Uploaded AIM software products, AIM workstation, ATB and ATS |

## Status of Milestones

| Milestone | Delivery Date | Status |
| --- | --- | --- |
| AIM 4.0 model | March 2013 | Updated and uploaded to production caDSR |
| AIM FY’13 design document |  | Ongoing |

## Work Planned for Next Month

| Activity | Description |
| --- | --- |
| AIM FY’13 Design | In progress |
| AIM 4.0 with CMake | In progress |
| AIM 4.0 workstation | In progress |
| AIM 4.0 RESTFul interface with AIM Data Service | In progress |
| AIM 4.0 XNAT | In progress |
| Bug fixes for AIM workstation, ATB and ATS | In progress |

## Travel Planned for Next Month

| Attendees | Travel Purpose | Description |
| --- | --- | --- |
| Not applicable |  |  |

# Issue Management

No issues at this time.

# Risk Management

| ID | Description | Owner | Potential Impact | Priority (H, M, L) | Status (Open, Closed) |
| --- | --- | --- | --- | --- | --- |
| 1 | NBIA and caGRID 1.4 test | CBIIT | Software development may not be fully working with the new NBIA and caGRID 1.4 | H | Open |

# External Dependencies

| Dependency | Date | Status | Comments |
| --- | --- | --- | --- |
| NBIA | Today - | Waiting | We are waiting for NBIA in order to test caGRID authentication in C#. |

# Status of Deliverables

See MS Project.