Northwestern University

# Monthly Status Report

Annotation and Image Markup (AIM)

12XS577

May 2013

Pattanasak Mongkolwat

p-mongkolwat@northwestern.edu

Reported: June 3, 2013

# Contents

Project Background/Objectives	2

Personnel Roster	2

Contract Overview	3

Current Project Status	3

Update AIM wiki pages	3

AIM 4.0 Library and Workstation	4

CMake and AIM 4.0 library	4

AIM 4.0 Workstation	4

XNAT	5

AIM 4.0 RESTFul interface with AIM Data Service	5

AIM on GitHub	5

The GitHub team from Ellumen informed the AIM team that the AIM source code and related materials on GitHub, https://github.com/NCIP/annotation-and-image-markup are available. The AIM team informed the GitHub team how to build AIM related products as follows.	5

Working with QA team	6

Description of Work Completed During the Month	6

External Meetings	6

Project Progress	9

Status of Milestones	9

Work Planned for Next Month	9

Travel Planned for Next Month	10

Issue Management	10

Risk Management	10

External Dependencies	10

Status of Deliverables	10

# Project Background/Objectives

The objective of this project is to continue to develop the Annotation and Imaging Markup (AIM) software library and tools based on the AIM v4.0 model to meet the challenge of targeted multiple imaging domains, including Radiology and Radiation Oncology. The AIM model establishes a solid foundation for the growth of AIM in specific areas such as clinical trials and life science. The AIM standard has demonstrated its usefulness by collecting the descriptive information of images with user-generated graphical symbols, computational results, and textual descriptors placed on the images in a single common information source. The AIM model is necessarily complex and comprehensive. Typically, users do not want to understand the model comprehensively. We consider AIM users as belonging to one of two types: end-user or software developer. We provide them with appropriate software products and a programming library along with a referenced implementation of the library.

The AIM template is designed to abstract the complexity and reduce the number of activities for both types of AIM users. A template consists of a collection of questions and corresponding answers to each question. It increases AIM usability and improves experiences for users who create AIM data in their specific domain areas.

The AIM template project has two components: AIM Template Builder (ATB) and AIM Template Service (ATS). ATB has been developed to allow creation and modification of AIM templates via a software application with a simple graphical user interface. A template constrains AIM users to consistently create structured AIM data with standardized semantic vocabulary and controlled terminologies. ATS allows AIM users to search, share, download, and upload their templates.

The outcome of the project includes the AIM 4.0 foundation model, AIM 4.0 imaging model for (but not limited to) Radiology and Oncology, AIM toolkit (library in C++ and a conversion tool), AIM workstation, and AIM template software. The AIM software products will enable imaging interpreters, image researchers, and associated sciences personnel from different domains to adopt standardized annotations and imaging markup in conducting their clinical trials and translation medicine research.

# Personnel Roster

| Personnel | Roles | Organization |
| --- | --- | --- |
| Pattanasak (Pat) Mongkolwat | Principal Investigator (PI), project manager and software engineer | Northwestern University |
| Vladimir Kleper | Researcher and software engineer | Northwestern University |
| Skip Talbot | Software engineer | Northwestern University |
| David Clunie | Consultant (DICOM, imaging and clinical expert) | PixelMed Publishing, LLC |
| Gregory Sharp | Consultant (CMake) | - |
| Daniel Rubin | Consultant (AIM and clinical expert) | Stanford University |
| Carolyn Klinger | Technical Writer | National Cancer Instittute |

# Contract Overview

The purpose of this project is to provide guidelines for extending the AIM model to enhance existing AIM tools (C++ toolkit, ATS and AIM for ClearCanvas workstation), develop additional AIM capabilities, and provide support in line with the historical workload and available resources.

The AIM project consists of the AIM information model, C++ Application Programming Interfaces (APIs), ATS, and AIM-enabled workstations. At the end of this research and development phase, we will accomplish the following.

- First, deliver a technical document on how to extend the AIM foundation model and library.

- Second, deliver the AIM C++ toolkit for Linux, OS X, and Windows platforms.

- Third, ATS shall have a Representational State Transfer (REST, RESTful conforms to REST constraints) APIs for other applications to consume ATS services.

- Fourth, AIM on ClearCanvas workstation will support creation and use of DICOM segmentation objects along with related AIM objects. The workstation will create and store AIM 4.0, import imaging studies from the eXtensible Neuroimaging Archive Toolkit (XNAT), communicate with AIM Data Service via RESTful APIs, validate markup creation and integrate a centralized imaging security service. An AIM plugin for the ClearCanvas workstation will be provided. A demonstration of the workstation installed on Amazon cloud will be provided.

- Fifth, AIM Data Object Service (DOS) will offer web services to create and manipulate AIM data.

The following tools were used in this project.

- Altova XMLSpy 2013 (Altova)

- Berkeley DB XML by Oracle

- Boost C++ library version 1.34.1 (Boost.org)

- caCORE SDK 4.1.1 (caBIG®)

- CMake 2.8.x and above

- DCMTK version 3.6.x (OFFIS e. V.)

- Eclipse (Eclipse Foundation, Inc.) for Windows and Linux

- Enterprise Architect version 10.x (Sparx Systems)

- Homebrew Package Installer for Mac OS X

- Java JDK 6 (Sun Microsystems)

- Linux OSes (Debian 6.0.x and above and Ubuntu version 11 and above)

- Mac OS X 10.7.5 (Lion)

- Microsoft Visual Studio 2008 and 2010 (Microsoft) with STL

- Xcode 4.6.x and Xcode command line utilities

- Xerces XML library version 3.0.1 (Apache Software Foundation)

# Current Project Status

## Update AIM wiki pages

We update the AIM pages on the NCI Wiki as needed.

## AIM 4.0 Library and Workstation

We are implementing the AIM 4.0 C++ library on the AIM 4.0 workstation. An alpha version has been given to the QA team to perform tests. We start implementing AIM 4.1 workstation at the end of May.

## CMake and AIM 4.0 library

Greg and the AIM team worked on the following issues during the first and second week of May.

  - Greg made the CMake configuration to follow the Windows convention (all caps) for one pre-processor definition.

  - Most of the platform configurations are done. He is performing a cleanup and will let us know soon when it's ready for testing on all platforms for shared and static builds.

  - Greg is going to post on the DCMTK forums and describe the issue we have with non-deterministic order of static log4cpp initialization on Linux and OSX. We currently work around that by disabling DCMTK's logging but doing so may not be an option for others when they use AIMLib in their projects.

  - During our next call we are going to review the overall progress of the project so far and check to see what is left to be done.

  - Next t-con is on May 9th, 2013.

During the third week of May, Greg and the AIM team performed the following tasks.

- Investigated the naming of DLL on Windows. We are determining whether or not we want to put the AIM version into the name of AIMLib dll.

- Build / prerequisites documentation is not complete.

- Make the release build the default.

- Test that the debug build works on all platforms.

- Install and uninstall targets for UNIX.

- In build instructions, describe building debug vs release.

- In build instructions, describe building 32 vs 64 on Windows.

- Next t-con is this coming Thursday.

- Questions for the next meeting is whether we need a 32-bit mac build?

    - To find out Mac OS X versionIn: uname -a

You may see something like this.

    - 32-bit:

Darwin iMac.local 10.0.0 Darwin Kernel Version 10.0.0: Fri Jul 31 22:47:34 PDT 2009; root:xnu-1456.1.25~1/RELEASE_I386 i386

    - 64-bit:

Darwin iMac.local 10.0.0 Darwin Kernel Version 10.0.0: Fri Jul 31 22:47:34 PDT 2009; root:xnu-1456.1.25~1/RELEASE_X86_64 x86_64

During the third week of May, Greg and the AIM team performed the following tasks.

- Investigate naming of DLL on windows to determine whether we want to put the AIM version into the name of AIMLib dll.

- Greg continues to work on the installation of the AIM library on a UNIX system.

## AIM 4.0 Workstation

The AIM team released an alpha AIM 4.0 workstation for testing purposes on May 17th. For AIM 4.0 Workstation, we finished the initial AIM 4.0 code migration and implementation. Previously existing workstation features like creation of annotations, reading templates, listing existing annotations, displaying content of existing annotations and importing annotations are implemented. The AIM team tested it before our team provided the QA analyst (Tin Tran) with the initial alpha build of the 4.0 Workstation. We'll need to continue testing it internally as well. The test build that Tin has also includes XNAT plugin.

## XNAT

The AIM team provided a XNAT live demonstration on AIM on ClearCanvas workstation to NCI’s AIM project officers and project manager. XNAT’s Dlls were sent to the QA team to test the implemented XNAT functionalities in mid May 2013.

## AIM 4.0 RESTFul interface with AIM Data Service

The AIM team continued to work with Emory as follows.

Week of May 5th, 2013.

- Sent Nadir the updated AIM Data Service requirements document with additional XPath examples.

- First version of AIM Data Service will come online on or about the 2nd week of May from Emory.

- The initial version of the new AIM Data Service will support Image Annotations only. We will talk about Annotation of Annotation support closer to the time when the workstation implements it. Annotation of Annotation AIM data service may have a different URL (TBD).

- AIM Data Service 2.0 only supports API Key STS authentication (no caGrid, a.k.a. Dorian support)

- The official name of the new Bindas-based AIM Data Service needs to be discussed with Ashish. Internally they call it AIME 2.0

- Before the AIM Data Service release, we will get a document with draft API, query conventions, and URLs. The final deployed version may have changes.

Week of May 13th, 2013.

- Nadia informed us that the first version of the service is ready for testing purposes.

- Will start integrating this week

Week of May 20th, 2013.

- Skip has been working on AIM Data Service 2.0.  He has the web service code in place and can authenticate with the STS, and retrieve and store the API key.

- Skip needs to create a GUI for STS.

Week of May 27th, 2013

- Skip is currently working on integrating the rest of the API with the GUI (making the data structures from the web service calls and binding them to the query results controls).

## AIM on GitHub

## The GitHub team from Ellumen informed the AIM team that the AIM source code and related materials on GitHub, https://github.com/NCIP/annotation-and-image-markup are available. The AIM team informed the GitHub team how to build AIM related products as follows.

AIMToolkit_v3.0.2_rv11 (CMake and MS Visual Studio 2008):

https://github.com/NCIP/annotation-and-image-markup/blob/master/AIMToolkit_v3.0.2_rv11/source/AIMLib/AIMLib.sln

AIMToolkit_v4.0.0_rv44:

Windows (CMake and MS Visual Studio 2008):

https://github.com/NCIP/annotation-and-image-markup/blob/master/AIMToolkit_v4.0.0_rv44/source/AIMLib/AIMLib.sln

Ubuntu (CMake and Make):

https://github.com/NCIP/annotation-and-image-markup/tree/master/AIMToolkit_v4.0.0_rv44/source/AIMLib

ATB_1.0_src (Maven):

https://github.com/NCIP/annotation-and-image-markup/blob/master/ATB_1.0_src/pom.xml

ATB_1.1_src (Maven):

https://github.com/NCIP/annotation-and-image-markup/blob/master/ATB_1.1_src/pom.xml

ATS_1.0_src (Ant):

https://github.com/NCIP/annotation-and-image-markup/blob/master/ATS_1.0_src/build.xml

ATS_1.1_src (Ant):

https://github.com/NCIP/annotation-and-image-markup/blob/master/ATS_1.1_src/build.xml

AimPlugin3.0.4 (MS Visual Studio 2008) (This project requires ClearCanvas SDK 2.0sp1, which may no longer be available from ClearCanvas):

https://github.com/NCIP/annotation-and-image-markup/blob/master/AimPlugin3.0.4/AimPlugin%203.0.4.sln

## Working with QA team

The AIM team started working with the QA team to test the AIM Workstation and CMake with the AIM 4.0 library.

  - Nadir continues to implement the AIM 4.0 Data Service. An initial version should be available in the first half of May.

  - Continue to work on ATS deployments in 32 and 64-bit.

  - Continue to work on workstation 3.5 and 4.0 test.

  - Continue to work on XNAT on workstation 4.0 test.

  - Continue to work on CMake test.

# Description of Work Completed During the Month

## External Meetings

| Date | Topic | Project Attendees (Optional) |
| --- | --- | --- |
| May 2013 | JIRA issues (addition and updates) | Pat, Vlad, Skip |
| May 2013 | Weekly telephone conference - Continued weekly report - Provided a demo XNAT capability - Provided a demo ANIVATR capability | Ed Helton, Jonathan Lin, Ulli Wagner, Laxmi, Tin, Vlad, Skip, Pat |
| May 2013 | Participate NCI Case Report Form Harmonization Working Group on Imaging | Pat |
| May 2013 | Work with QA team at NCI - Exchanged and answered e-mails related to AIM tools and products - ATS authentication did not work because the STS service was down. - ATS configuration, folder name on Unix shall not include space in a directory path. - How-to use XNAT to import imaging studies - Exchanged e-mails about AIM & CMake Test - Test environment - Test instructions - Telephone conference - Web conferencing with Tin and showed him how to test AIM 4.0 workstation - Sent XNAT DLLs and installation instructions for testing purposes. - Tin reported an IE 8 problem with the XNAT website. This is an incompatibility problem between XNAT site and IE 8. We will need to request Workstation users to have at least IE 9 on their systems. - Worked on the XNAT download icon notification - Changed the notification language per Tin’s suggestions - Fixed create an AIM instance with a template that does not show any questions to AIM user - Sent AIM CMake library for testing purposes - Answered questions about ATS 1.1 security issues | Tin, Vlad, Skip and Pat |
| May 2013 | Worked with Carolyn Klinger on - AIM monthly report - Corrected incorrect URLs (e.g. AIM Workstation) - Worked on AIM 3.5 and 4.0 user’s guide - Worked on release notes for 3.5.0.1 | Carolyn Klinger and Pat |
| May 2013 | Worked with Gregory Sharp on CMake - Telephone conferences - Exchanged e-mails compiling Windows, Linux and Mac OS X related issues | Gregory Sharp, Vlad Kleper, Pat |
| May 2013 | Work with Emory team on AIM Data Service - Responded to JAXB beans for AIM 4.0 model. Suggested to get it from Lawrence Tarbox at Washington University at St. Louis - Vlad provided information about ImageStudy (ImageAnnotation vs. ImageAnnotationCollection) - Nadir provided AIM Data Service 2.0 for the AIM team to test. http://imaging.cci.emory.edu/wiki/display/CXFIVIM/AIME+-+ClearCanvas+Integration | Ashish, Nadir, Vlad, Skip and Pat |
| May 2013 | - Contacted David about the plan to implement DICOM Segmentation on AIM workstation. We will start a meeting after SIIM 2013 meeting. | David Clunie and Pat |
| May 2013 | Worked with Justin Kirby (CIP) - AIM Workstation 3.5 anatomic entity label does not display when “Should Display” set to “False”. Justin wants to have the label stay on all the time. - Exchanged e-mails with Justin and John about AIM plug-in on ClearCanvas zero footprint diagnostic workstation. | Justin Kirby, John Freymann, Skip and Pat |
| May 2013 | Worked with NBIA team on retrieving imaging studies from NBIA - Exchanges e-mails with Qinyan about NBIA retrieval errors. This problem was identified by the NBIA team and fixed it before. https://tracker.nci.nih.gov/browse/NBIA-600 - A NBIA member needs to set a permission for a temporary zip file to be created for image transfer purposes | Qinyan Pan, Tin Tran and Pat |
| May 2013 | Worked with NBIA team on retrieving imaging studies from NBIA - Exchanged e-mails - Received a notification about having AIM source code and related documents on GitHub under https://github.com/NCIP/annotation-and-image-markup - Responded to Qinyan about building AIM related products. She will work with Tin Tran on ATS build. - Sent e-mails about AIM-related products | Qinyan Pan, Scott Gustafson, Yogesh Prasai and Pat |
| May 2013 | - Consulted about AIM Template Builder 2.0 - Provided AIM 2.0 template examples - Answered question about how to validate manually-created AIM template documents - Answered question about the AIM Workstation - Answered question about AIM Data Service | Daniel Rubin, Debra Willrett and Vlad |
| May 2013 | Informed the XNAT leader about invalid incorrect DICOM header UIDs. - The AIM team found a problem when we tried to import imaging studies from mBIRN collection - Dan informed us that he has no control of data since XNAT is an open platform. He will introduce a good practice guideline for submitting studies to public XNAT. | Dan Marcus, Pat |
| May 2013 | Worked with NBIA team on GitHub - Answered Scott’s e-mail about copyright and DCMTK | Scott Gustafson, Qinyan Pan, Ulli, Vlad, Pat |
| May 2013 | Worked with SAIC-F project managers - Submitted AIM poster for approval by SAIC-F - Requested the use of NCIP logo on the poster | Ulli, Alex Konev, Pat |
| May 2013 | Participated in TCIA REST API conference call - Participated in TCIA REST API conference calls - Received API Key - Created a C# program to test the TCIA RESTful interface and the API Key. - Sent a response and requests to TCIA team to improve TCIA interface and capabilities | Pat, Vlad and Skip |

## Project Progress

| Activity | Description |
| --- | --- |
| NCI’s JIRA | Continue updating: - AIM Enterprise Service (ATB & ATS), https://tracker.nci.nih.gov/browse/AIMES - AIM Model, https://tracker.nci.nih.gov/browse/AIMWS - AIM Workstation, https://tracker.nci.nih.gov/browse/AIM |
| AIM SVN for GitHub | - Uploaded AIM 3.0, AIM foundation, AIM 4.0 and related source code to the models - Uploaded related XML schemas, documents - Uploaded AIM software products, AIM workstation, ATB and ATS |

## Status of Milestones

| Milestone | Delivery Date | Status |
| --- | --- | --- |
| AIM FY’13 design document |  | Ongoing |

## Work Planned for Next Month

| Activity | Description |
| --- | --- |
| AIM FY’13 Design | In progress |
| AIM 3.5.0.1 workstation (see workstation JIRA) | Delivered a beta version for QA |
| AIM 4.0 with CMake | In progress |
| AIM 4.0 workstation | Delivered a beta version for QA |
| AIM 4.0 RESTFul interface with AIM Data Service | In progress |
| AIM 4.0 XNAT | Delivered a beta version for QA |
| Bug fixes for AIM workstation, ATB and ATS | In progress |

## Travel Planned for Next Month

| Attendees | Travel Purpose | Description |
| --- | --- | --- |
| Not applicable |  |  |

# Issue Management

No issues at this time.

# Risk Management

| ID | Description | Owner | Potential Impact | Priority (H, M, L) | Status (Open, Closed) |
| --- | --- | --- | --- | --- | --- |
| 1 | NBIA and caGRID 1.4 test | NCIP | Software development may not be fully working with the new NBIA and caGRID 1.4 | H | Open |

# External Dependencies

| Dependency | Date | Status | Comments |
| --- | --- | --- | --- |
| NBIA | Today - | Waiting | We are waiting for NBIA in order to test caGRID authentication in C#. |

# Status of Deliverables

See MS Project.